## Project Costing Model
Project Costing Overview
Project Variables |  | Project Duration
Software Manuals | 13 | Total effort (hours) | 13000
Man Hours per Manual | 1000 | Total working week (hours) | 400
Total staff | 10 | Calculated duration (weeks) | 32.5
Working day (hours) | 8
Working week (days) | 5 | Salary calculations (per person per week)
Standard Work Week Hours | 35 | Total hours per week | 40
Standard Hourly Rate | 50 | Base salary ($50 per hour up to 40 hours per week) | 2000
Overtime Hourly Rate | 75 | Overtime salary ($75 per hour over 40 hours per week) | 375
Costs |  | Revenues
Weekly salary (per person) | 2375 | Sale Price | 35
Total weekly salaries | 23750 | Quantity Sold (Per Manual) | 2140
Total project salaries | 771875 | Per Manual Revenue | 74900
Fixed Overheads | 100000 | Total Revenue | 973700
Total Project Costs | 871875 | Projected Profit | 101825

## Scenario Summary
Scenario Summary
|  | Current Values: | Current Price | Price Decrease | Price Increase
|  |  | Modified by Priyanka on 06-08-2021 | Modified by Priyanka on 06-08-2021 | Modified by Priyanka on 06-08-2021
Changing Cells:
| Sale_Price | 35 | 35 | 30 | 40
| Quantity_Sold__Per_Manual | 2140 | 2140 | 2461 | 1819
Result Cells:
| Projected_Profit | 101825 | 101825 | 87915 | 74005
Notes: Current Values column represents values of changing cells at
time Scenario Summary Report was created. Changing cells for each
scenario are highlighted in gray.

## Solver Summary
Scenario Summary
|  | Current Values: | 20 Weeks | 30 Weeks | 21 Weeks | 42 Weeks
|  |  | Created by Mr Prashan Karunaratne on 9/25/2017 | Created by Mr Prashan Karunaratne on 2017-09-25 | Created by Mr Prashan Karunaratne on 9/25/2017 | Created by Mr Prashan Karunaratne on 9/25/2017
Changing Cells:
| Total_Staff | 10 | 11.4471 | 10 | 12 | 10
| Working_Day | 6.8 | 9.1577 | 8 | 8 | 6.8
| Working_Week | 4.25 | 5.7236 | 5 | 6 | 4.25
Result Cells:
| Projected_Profit | 198800 | -100225.4239 | 86300 | -44950 | 198800
Notes: Current Values column represents values of changing cells at
time Scenario Summary Report was created. Changing cells for each
scenario are highlighted in gray.